Meeting Minutes

## Meeting 1 – Initial Project Discussion

Date: 27 February 2026
Attendees: Cheok En Qi, Teong Sze Ching

Agenda

- Discuss project topic and scope

- Plan initial project tasks and responsibilities

Key Discussion Points

- Our group had a very brief discussion to find dataset for the group project when Prof released the group project description before the 1st official meeting happens. That discussion was not recorded since it was a 5-minute face to face talk.

- The group agreed to use the dataset from CEIC, focusing on Singapore Fertility Trends as the project topic due to its relevance to current demographic issues.

- Key variables identified include Total Fertility Rate (TFR), marriage rates, divorce rates, and age-specific fertility rates.

- The group discussed using visual analytics and statistical analysis to examine potential relationships between these variables.

Decisions Made

- Project title confirmed: Singapore Fertility Trends: A Visual Analytics Study

- Both members work on data cleaning and regroup on 3 March 2026 to share their EDA steps

Meeting 2 – Project Progress Review

Date: 3 March 2026
Attendees: Cheok En Qi, Teong Sze Ching

Agenda

- Review progress on data cleaning

- Discuss early observations from the data (EDA)

- Plan next analytical steps

Key Discussion Points

- Data cleaning was completed for the dataset.

- Initial exploratory analysis revealed a declining fertility trend in recent years.

- The group discussed possible lag effects, where changes in marriage trends may influence fertility outcomes after several years.

- Visualisation approaches for the project website were also discussed, and the group agreed on the colour tone of the website.

Decisions Made

- Both members would proceed with EDA, while ensuring that their work did not overlap.

- The group agreed to prioritise correlation and regression analysis over time-series forecasting, in order to focus on the exploratory and explanatory analysis of fertility trends and their relationships with marriage and divorce indicators.

- En Qi would proceed with correlation analysis to examine relationships between fertility, marriage, and divorce indicators.

- Sze Ching would proceed with regression analysis.

- Both members would work on storyboarding.

- The group would regroup on 14 March 2026.

Meeting 3 – Project Development review

Date: 14 March 2026
Attendees: Cheok En Qi, Teong Sze Ching

Agenda

- Review progress on EDA, analysis pages, storyboarding

- Plan Shiny App development

- Build website for project proposal submission

Key Discussion Points

- Correlation analysis results showed several moderate relationships between fertility and marriage indicators.

- Regression analysis was progressing, focusing on understanding statistical associations between demographic variables and fertility trends.

- The group agreed to structure the Shiny App into multiple sections:

  - Home Page

  - EDA Page

  - Correlation Analysis Page

  - Regression Analysis Page

Decisions Made

- Enqi built the project proposal website on the same day and incorporated the information into the website.

- For shiny app development: En Qi would develop the Home Page and Correlation Page. Sze Ching would develop the EDA Page and Regression Page.

Meeting 4 –  Urgent Meeting

Date: 21 March 2026
Attendees: Cheok En Qi, Teong Sze Ching

Agenda

- Address professor’s feedback on analytical methods

Key Discussion Points

- The project was flagged as high risk due to mismatches between the dataset and analytical methods used.

- Current methods (general regression and correlation analysis) are not suitable for time series data.

- Recommended changes by Prof:

  - Replace general regression with panel regression

  - Replace correlation analysis with cross-correlation analysis

- Tools/packages suggested by professor:

  - TStusio (for cross-correlation)

  - ExPanDaR and plm R packages (for panel regression)

Decisions Made

- Implement panel regression and cross-correlation analysis

- Explore and apply recommended tools (TStusio, ExPanDaR, plm)

Meeting 5 – Final Submission Preparation

Date: 28 March 2026
Attendees: Cheok En Qi, Teong Sze Ching

Agenda

- Finalise project items

- Prepare poster

Key Discussion Points

- The Shiny App components were integrated into the project website.

- The group reviewed the visualisations and ensured that the analysis clearly communicates the key findings.

- Poster design were discussed.

Decisions Made

- Final website structure confirmed.

- Poster content finalised and both will work on it to submit tonight.

- Complete final checks on the website and analysis.

- Submit the project before the deadline.