## Sheet1
Tasks | PIC | Dates (27 Feb - 1 Apr)
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
1st Project Discussion | All | bar: Dates (27 Feb - 1 Apr) 27
Project Proposal
Data Cleaning | All | bar: Dates (27 Feb - 1 Apr) 28 to Dates (27 Feb - 1 Apr) 1
EDA | All | bar: Dates (27 Feb - 1 Apr) 2 to Dates (27 Feb - 1 Apr) 5
Correlation | Enqi | bar: Dates (27 Feb - 1 Apr) 6 to Dates (27 Feb - 1 Apr) 11
Regression | Sze Ching | bar: Dates (27 Feb - 1 Apr) 6 to Dates (27 Feb - 1 Apr) 11
StoryBoard | All | bar: Dates (27 Feb - 1 Apr) 12 to Dates (27 Feb - 1 Apr) 13
Group Project website creation | Enqi | bar: Dates (27 Feb - 1 Apr) 14
Shiny App
Home page | Enqi | bar: Dates (27 Feb - 1 Apr) 15 to Dates (27 Feb - 1 Apr) 28
EDA page | Sze Ching | bar: Dates (27 Feb - 1 Apr) 15 to Dates (27 Feb - 1 Apr) 28
Correlation page | Enqi | bar: Dates (27 Feb - 1 Apr) 15 to Dates (27 Feb - 1 Apr) 28
Regression page | Sze Ching | bar: Dates (27 Feb - 1 Apr) 15 to Dates (27 Feb - 1 Apr) 28
Final Submission
Meeting Minutes | All | bar: Dates (27 Feb - 1 Apr) 27; Dates (27 Feb - 1 Apr) 2; Dates (27 Feb - 1 Apr) 14; Dates (27 Feb - 1 Apr) 28
Poster | All | bar: Dates (27 Feb - 1 Apr) 28 to Dates (27 Feb - 1 Apr) 1